## Gantt Chart
| Visor |  |  |  | Visor
| Betram Lalusha |  |  |  | 2024-02-20
TASK TITLE | Time(Days) | Preds | [10 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FOUR
|  |  | Jan 1 - Jan 5 |  |  |  |  | Jan 8 - Jan 12 |  |  |  |  | Jan 15 - Jan 19 |  |  |  |  | Jan 22 - Jan 26 |  |  |  |  | Jan 29 - Feb 2 |  |  |  |  | Feb 5 - Feb 9 |  |  |  |  | Feb 12 - Feb 16 |  |  |  |  | Feb 19 - Feb 23 |  |  |  |  | Feb 26 - Mar 1 |  |  |  |  | Mar 4 - Mar 8 |  |  |  |  | Mar 11 - Mar 15 |  |  |  |  | Mar 18 - Mar 22 |  |  |  |  | Mar 25 - Mar 29 |  |  |  |  | April 1- April 5 |  |  |  |  | April 8 - April 12 |  |  |  |  | April 15 - April 19 |  |  |  |  | April 22 - April 26 |  |  |  |  | April 29 - May 3
|  |  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Start | 0 | -- | bar: Jan 1 - Jan 5 W to Jan 1 - Jan 5 F
A. Open Cemera Button | 12 | Start | bar: Jan 1 - Jan 5 M to Jan 15 - Jan 19 T
B. Bug Fix: Checking into places | 7 | -- | bar: Jan 1 - Jan 5 M to Jan 8 - Jan 12 W
C. Bug Fix: Load time for async images too long | 7 | B | bar: Jan 1 - Jan 5 M to Jan 15 - Jan 19 R
D. Bug Fix: Reloading Posts every time view appears | 5 | C | bar: Jan 15 - Jan 19 F to Jan 22 - Jan 26 R
E. SimilarQuestions View | 19 | -- | bar: Jan 1 - Jan 5 M to Jan 22 - Jan 26 R
F. PlacesWithItemView | 10 | E | bar: Jan 22 - Jan 26 F to Feb 5 - Feb 9 R
G. Replying to replies | 15 | -- | bar: Jan 1 - Jan 5 M to Jan 22 - Jan 26 M
H. Upvote/Downvote count | 7 | G | bar: Jan 22 - Jan 26 T to Jan 29 - Feb 2 W
I. BugFix: Date posted formatting | 9 | D | bar: Jan 22 - Jan 26 F to Feb 5 - Feb 9 R
J. Persistence | 30 | I | bar: Feb 5 - Feb 9 F to Mar 18 - Mar 22 R
Finish | -- | J | bar: April 29 - May 3 F